## Slide 1: Brightwell Analytics — 2027 Product Roadmap
Product all-hands · Presented by Maya Okafor, VP Product

## Slide 2: Where we are
42,000 active workspaces, up 31% year over year
Top requests: real-time dashboards, data alerts, a mobile app
Churn is highest in the first 30 days: onboarding is the gap

## Slide 3: Q1 2027 — Faster onboarding
Guided setup that connects a first data source in under 5 minutes
Template gallery with 20 starter dashboards
Owner: Daniel Reyes, Onboarding team
Success measure: 30-day retention from 71% to 80%

## Slide 4: Q2 2027 — Real-time dashboards
Streaming connectors for Postgres, Kafka and webhooks
Dashboards refresh every 5 seconds instead of every hour
Owner: Priya Natarajan, Data Platform
Beta with 50 customers in May

## Slide 5: Q3 2027 — Alerts and mobile
Threshold and anomaly alerts by email, Slack and push
iOS and Android apps for viewing dashboards and alerts
Owners: Tom Becker (alerts), Ana Lima (mobile)

## Slide 6: Roadmap at a glance
Quarter | Theme | Owner | Status
Q1 | Faster onboarding | Daniel Reyes | In design
Q2 | Real-time dashboards | Priya Natarajan | Building
Q3 | Alerts | Tom Becker | Planned
Q3 | Mobile apps | Ana Lima | Planned
Q4 | AI-written insights | TBD | Exploring

## Slide 7: Risks and open questions
Streaming costs could double our cloud bill: pricing review in February
Mobile needs two engineers we haven't hired yet
AI-written insights depend on the data-privacy review (Legal, March)